## Budget Summary
DESIGNED & BUILT ¦ PROJECT BUDGET WORKSHEET
Track the budget, commitments, and forecast without the complexity of a contractor estimate.
Project Name | 2,500 SF Ohio Single-Family House - Test Estimate |  |  | Date | 2026-10-20
Project Location | Ohio (statewide planning assumption) |  |  | Project Status | Concept Budget
Owner / Client | Illustrative Test Case |  |  | Total Project SF | 2500
PROJECT SUMMARY
Current Budget | 734000 | Committed | 0 | Forecast Final | 734000 | Budget Variance | 0
Category | Original Budget | Approved Changes | Current Budget | Committed | Forecast to Complete | Forecast Final | Variance
HARD COSTS
General Conditions | 50000 | 0 | 50000 | 0 | 50000 | 50000 | 0
Site Work & Demolition | 35000 | 0 | 35000 | 0 | 35000 | 35000 | 0
Structure | 80000 | 0 | 80000 | 0 | 80000 | 80000 | 0
Carpentry & Framing | 95000 | 0 | 95000 | 0 | 95000 | 95000 | 0
Building Envelope / Roofing | 70000 | 0 | 70000 | 0 | 70000 | 70000 | 0
Doors / Windows / Glazing | 45000 | 0 | 45000 | 0 | 45000 | 45000 | 0
Interior Construction & Finishes | 105000 | 0 | 105000 | 0 | 105000 | 105000 | 0
Mechanical / Plumbing / Electrical | 90000 | 0 | 90000 | 0 | 90000 | 90000 | 0
Fire Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site / Exterior Improvements | 30000 | 0 | 30000 | 0 | 30000 | 30000 | 0
Hard Costs Subtotal | 600000 | 0 | 600000 | 0 | 600000 | 600000 | 0
SOFT COSTS
Architecture & Engineering | 42000 | 0 | 42000 | 0 | 42000 | 42000 | 0
Survey / Geotechnical | 6000 | 0 | 6000 | 0 | 6000 | 6000 | 0
Permits / Plan Review | 8000 | 0 | 8000 | 0 | 8000 | 8000 | 0
Testing / Inspections | 3000 | 0 | 3000 | 0 | 3000 | 3000 | 0
Insurance / Legal / Financing | 5000 | 0 | 5000 | 0 | 5000 | 5000 | 0
Soft Costs Subtotal | 64000 | 0 | 64000 | 0 | 64000 | 64000 | 0
OWNER COSTS
Furniture, Fixtures & Equipment | 12000 | 0 | 12000 | 0 | 12000 | 12000 | 0
Technology / AV / Security | 5000 | 0 | 5000 | 0 | 5000 | 5000 | 0
Moving / Relocation | 3000 | 0 | 3000 | 0 | 3000 | 3000 | 0
Other Owner Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0
Owner Costs Subtotal | 20000 | 0 | 20000 | 0 | 20000 | 20000 | 0
ALLOWANCES & CONTINGENCY
Construction Contingency | 30000 | 0 | 30000 | 0 | 30000 | 30000 | 0
Owner Contingency | 20000 | 0 | 20000 | 0 | 20000 | 20000 | 0
Allowances | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allowances & Contingency Subtotal | 50000 | 0 | 50000 | 0 | 50000 | 50000 | 0
TOTAL PROJECT BUDGET | 734000 | 0 | 734000 | 0 | 734000 | 734000 | 0
Budget / SF | 293.6 |  | Forecast / SF | 293.6
ALTERNATES / OPTIONS
Description | Add / Deduct | Amount | Status | Budget Impact | Notes
0
0
0
BUDGET NOTES / ASSUMPTIONS
ILLUSTRATIVE TEST ESTIMATE - NOT A BID. Budget values on this sheet now roll up automatically from Cost Detail by category. To revise the estimate, edit or add lines on Cost Detail. Assumes a 2,500 SF finished single-family home in Ohio, moderate/custom quality, conventional construction, normal site conditions, and public utilities. Land acquisition and financing interest are excluded.
Note on B14: Planning benchmark informed by 2026 Ohio published custom-home ranges of roughly $220-$300+/SF, excluding land; test case uses $240/SF hard construction as a moderate custom planning assumption. Sources: https://homeguide.com/costs/cost-to-build-a-house-in-ohio ; https://lemmoncustomhomes.com/cost-per-square-foot-to-build-a-house

## Cost Detail
DESIGNED & BUILT ¦ COST DETAIL REGISTER | [10 empty] | General Conditions
Enter project line items here. Budget Summary automatically rolls up totals by Category. | [10 empty] | Site Work & Demolition
Structure
Category | Description | Vendor / Contractor | Original Budget | Approved Changes | Current Budget | Committed | Paid to Date | Forecast to Complete | Forecast Final | Notes | Carpentry & Framing
General Conditions | Concept budget allowance | Planning estimate | 50000 | 0 | 50000 | 0 | 0 | 50000 | 50000 | Seeded from verified 2,500 SF Ohio test estimate. | Building Envelope / Roofing
Site Work & Demolition | Concept budget allowance | Planning estimate | 35000 | 0 | 35000 | 0 | 0 | 35000 | 35000 | Seeded from verified 2,500 SF Ohio test estimate. | Doors / Windows / Glazing
Structure | Concept budget allowance | Planning estimate | 80000 | 0 | 80000 | 0 | 0 | 80000 | 80000 | Seeded from verified 2,500 SF Ohio test estimate. | Interior Construction & Finishes
Carpentry & Framing | Concept budget allowance | Planning estimate | 95000 | 0 | 95000 | 0 | 0 | 95000 | 95000 | Seeded from verified 2,500 SF Ohio test estimate. | Mechanical / Plumbing / Electrical
Building Envelope / Roofing | Concept budget allowance | Planning estimate | 70000 | 0 | 70000 | 0 | 0 | 70000 | 70000 | Seeded from verified 2,500 SF Ohio test estimate. | Fire Protection
Doors / Windows / Glazing | Concept budget allowance | Planning estimate | 45000 | 0 | 45000 | 0 | 0 | 45000 | 45000 | Seeded from verified 2,500 SF Ohio test estimate. | Site / Exterior Improvements
Interior Construction & Finishes | Concept budget allowance | Planning estimate | 105000 | 0 | 105000 | 0 | 0 | 105000 | 105000 | Seeded from verified 2,500 SF Ohio test estimate. | Architecture & Engineering
Mechanical / Plumbing / Electrical | Concept budget allowance | Planning estimate | 90000 | 0 | 90000 | 0 | 0 | 90000 | 90000 | Seeded from verified 2,500 SF Ohio test estimate. | Survey / Geotechnical
Fire Protection | Concept budget allowance | Planning estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Seeded from verified 2,500 SF Ohio test estimate. | Permits / Plan Review
Site / Exterior Improvements | Concept budget allowance | Planning estimate | 30000 | 0 | 30000 | 0 | 0 | 30000 | 30000 | Seeded from verified 2,500 SF Ohio test estimate. | Testing / Inspections
Architecture & Engineering | Concept budget allowance | Planning estimate | 42000 | 0 | 42000 | 0 | 0 | 42000 | 42000 | Seeded from verified 2,500 SF Ohio test estimate. | Insurance / Legal / Financing
Survey / Geotechnical | Concept budget allowance | Planning estimate | 6000 | 0 | 6000 | 0 | 0 | 6000 | 6000 | Seeded from verified 2,500 SF Ohio test estimate. | Furniture, Fixtures & Equipment
Permits / Plan Review | Concept budget allowance | Planning estimate | 8000 | 0 | 8000 | 0 | 0 | 8000 | 8000 | Seeded from verified 2,500 SF Ohio test estimate. | Technology / AV / Security
Testing / Inspections | Concept budget allowance | Planning estimate | 3000 | 0 | 3000 | 0 | 0 | 3000 | 3000 | Seeded from verified 2,500 SF Ohio test estimate. | Moving / Relocation
Insurance / Legal / Financing | Concept budget allowance | Planning estimate | 5000 | 0 | 5000 | 0 | 0 | 5000 | 5000 | Seeded from verified 2,500 SF Ohio test estimate. | Other Owner Costs
Furniture, Fixtures & Equipment | Concept budget allowance | Planning estimate | 12000 | 0 | 12000 | 0 | 0 | 12000 | 12000 | Seeded from verified 2,500 SF Ohio test estimate. | Construction Contingency
Technology / AV / Security | Concept budget allowance | Planning estimate | 5000 | 0 | 5000 | 0 | 0 | 5000 | 5000 | Seeded from verified 2,500 SF Ohio test estimate. | Owner Contingency
Moving / Relocation | Concept budget allowance | Planning estimate | 3000 | 0 | 3000 | 0 | 0 | 3000 | 3000 | Seeded from verified 2,500 SF Ohio test estimate. | Allowances
Other Owner Costs | Concept budget allowance | Planning estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Seeded from verified 2,500 SF Ohio test estimate.
Construction Contingency | Concept budget allowance | Planning estimate | 30000 | 0 | 30000 | 0 | 0 | 30000 | 30000 | Seeded from verified 2,500 SF Ohio test estimate.
Owner Contingency | Concept budget allowance | Planning estimate | 20000 | 0 | 20000 | 0 | 0 | 20000 | 20000 | Seeded from verified 2,500 SF Ohio test estimate.
Allowances | Concept budget allowance | Planning estimate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Seeded from verified 2,500 SF Ohio test estimate.
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0

## Read Me
HOW TO USE THIS WORKBOOK
1 | Start on Cost Detail Enter each budget line, bid, contract, purchase order, allowance, or owner cost. Select a Category from the dropdown.
2 | Budget Summary rolls up automatically Original Budget, Approved Changes, Committed, and Forecast to Complete are totaled from Cost Detail by Category. Do not type over the linked summary cells.
3 | Watch the variance Current Budget = Original Budget + Approved Changes. Forecast Final = Committed + Forecast to Complete. Variance = Current Budget - Forecast Final.
4 | Use one or many detail lines per category Add as much detail as you need. Multiple line items with the same Category will automatically combine on Budget Summary.
5 | Keep alternates separate Use the Alternates / Options section for add/deduct items until accepted. Once approved, add the amount as an Approved Change on the appropriate Cost Detail line.
Color key: Blue = user input ¦ Green = linked roll-up ¦ Black = formula ¦ Gray = labels / static text